## Table-1
Road Name: Banar Bhopalgarh Kuchera (SH 63)
SN | Package No | Name of Highways | Contract Amount (INR Cr.) | Appointed date | Contract Amount after (COS) | Scheduled date of completion | Extended date of completion | EOT | Total awarded length (km) | Total length after COS (km) | Completed length (km) | Payment made excl. Price Adj. (Rs. Cr. | Physical progress in terms of Financial | Financial Progress based on actual expenditure | Date of completion (Date issue of provisional comp. certificate)
1 | WB/RSHDP-II/EPC/01 | Banar Bhopalgarh Kuchera (SH 63) | 207.11 | 2018-06-01 | 207.11 | 2019-09-03 |  |  | 126.5 | 126.5 |  | 198.82 | 9.93 | 96

## Table-2
Road Name: Banar Bhopalgarh Kuchera (SH 63)
SN | Item | Scope | Completed (Last month) | Inprogress (Last month) | Completed (This month) | Inprogress (This month) | Completed (Till Date) | Inprogress (Till Date) | Not Started (Till Date)
1 | 5th km stone | 1 | 1 |  |  |  | 1 | 0 | 0
2 | Bus shelter including Solar Light | 30 | 28 |  |  |  | 28 | 0 | 2
3 | Conduit chamber | 1 | 1 |  |  |  | 1 | 0 | 0
4 | Culvert | 134 | 132 |  |  |  | 132 | 0 | 2
5 | Hecto meter stone | 1 | 1 |  |  |  | 1 | 0 | 0
6 | km stone | 1 | 1 |  |  |  | 1 | 0 | 0
7 | Major Junction | 11 | 11 |  |  |  | 11 | 0 | 0
8 | Minor Bridge | 2 | 2 |  |  |  | 2 | 0 | 0
9 | Minor Junction | 59 | 59 |  |  |  | 59 | 0 | 0
10 | Pipe culvert | 1 | 1 |  |  |  | 1 | 0 | 0
11 | Rain water harvesting | 253 | 253 |  |  |  | 253 | 0 | 0
12 | Road Boundary stone | 1 | 1 |  |  |  | 1 | 0 | 0
13 | Road sign | 1 | 1 |  |  |  | 1 | 0 | 0
14 | safety and traffic management during construction | 1 | 1 |  |  |  | 1 | 0 | 0
15 | Toll plaza | 3 | 3 |  |  |  | 3 | 0 | 0
16 | Toll Plaza (COS) | 3 | 2 |  |  |  | 2 | 0 | 1
17 | Utility Services | 1 | 1 |  |  |  | 1 | 0 | 0
18 | Road side plantation | 1 |  | 1 |  |  | 0 | 1 | 0
19 | Culvert COS | 3 |  |  |  |  | 0 | 0 | 3

## Table-3
Road Name: Banar Bhopalgarh Kuchera (SH 63)
SN | Item | Scope | Completed (Last month) | Completed (This month) | Completed (Till Date) | Balance

## Table-4
Road Name: Banar Bhopalgarh Kuchera (SH 63)
SN | Item | Scope | Completed (Last month) | Completed (This month) | Completed (Till Date) | Balance

## Table-5
Road Name: Banar Bhopalgarh Kuchera (SH 63)
SN | Items | Cost as per schedule H (INR Cr.) | Executed till previous month (INR Cr.) | Progress During this month (INR Cr.) | Up to this month (INR Cr.) | Progress achieved (%)
1 | (other items) | 44.65 | 2.4 |  | 2.4 | 5.38
2 | Minor Bridge/Underpass/overpass | 0.97 | 0.65 |  | 0.65 | 66.6
3 | Minor Bridges/Underpass/Overpass | 0.97 | 0.33 |  | 0.33 | 33.4
4 | other item | 44.65 | 0.01 |  | 0.01 | 0.03
5 | other items | 44.65 | 0.36 |  | 0.36 | 0.81
6 | Other Work 4 (b) other items | 44.65 | 2.46 |  | 2.46 | 5.52
7 | Other Work 4( a) Project Facility | 44.65 | 3.92 |  | 3.92 | 8.78
8 | Other Work Other Item 4(b) | 44.65 | 0.54 |  | 0.54 | 1.21
9 | Other Works | 44.65 | 4.79 |  | 4.79 | 10.72
10 | Other Works 4 (b) Other item | 44.65 | 2.97 |  | 2.97 | 6.66
11 | Others items | 44.65 | 2.13 |  | 2.13 | 4.77

## Table-6
Road Name: Banar Bhopalgarh Kuchera (SH 63)
SN | Package | Awarded Amount | Payment (Last month) | Payment (This month) | Payment (Till Date) | Financial Progress (%)
1 | WB/ RSHDP II/ANNUITY 01 | 210.11 | 121.76 |  | 121.76 | 57.95
2 | WB/ RSHDP II/ANNUITY 02 | 277 | 138.85 |  | 138.85 | 50.13
3 | WB/ RSHDP II/ANNUITY 03 | 130.66 | 70.45 |  | 70.45 | 53.92
4 | WB/ RSHDP II/ANNUITY 04 | 247.77 | 108.56 |  | 108.56 | 43.81
5 | WB/RSHDP-II/EPC/01 | 207.11 | 227.2 |  | 227.2 | 109.7
6 | WB/RSHDP-II/EPC/02 | 101.74 | 111.77 |  | 111.77 | 109.86
7 | WB/RSHDP-II/EPC/03 | 304.11 | 314.22 |  | 314.22 | 103.32
8 | WB/RSHDP-II/EPC/04 | 241 | 265.74 |  | 265.74 | 110.27
9 | WB/RSHDP-II/EPC/05 | 157 | 155.53 |  | 155.53 | 99.06
10 | WB/RSHDP-II/EPC/06 | 136 | 139.22 |  | 139.22 | 102.37
11 | Blackspot | 1 |  |  | 0 | 0
12 | RSHDP-II/WB-Tr-2/EPC-01 | 317.51 |  |  | 0 | 0
13 | RSHDP-II/WB-Tr-2/EPC-02 | 137.68 |  |  | 0 | 0
14 | RSHDP-II/WB-Tr-2/EPC-03 | 105 |  |  | 0 | 0

## Table-7
Road Name: Banar Bhopalgarh Kuchera (SH 63)
SN | Road | Plantation | Survival
1 | Banar Bhopalgarh Kuchera (SH 63) | 1649 | 300

## Table-8
Road Name: Banar Bhopalgarh Kuchera (SH 63)
SN | Package Name | Description | Milestone1 | Milestone2 | Milestone3 | Milestone4
1 | WB/RSHDP-II/EPC/01 | Contractual | 24-09-2018 | 17-01-2019 | 12-05-2019 | 04-09-2019
2 | WB/RSHDP-II/EPC/01 | EOT NO-1 | 24-09-2018 | 17-01-2019 | 12-05-2019 | 05-11-2019
3 | WB/RSHDP-II/EPC/01 | EOT NO-2 | 01-05-2019 | 01-11-2019 | 02-09-2020 | 13-06-2020
4 | WB/RSHDP-II/EPC/01 | EOT NO-3 | 01-05-2019 | 01-11-2019 | 18-11-2020 | 19-10-2020
5 | WB/RSHDP-II/EPC/01 | ACHEIVED DATE | 01-05-2019 | 01-11-2019 | 18-11-2020 | 19-10-2020
6 | WB/RSHDP-II/EPC/02 | Contractual | 13-10-2018 | 05-02-2019 | 14-08-2019 | 23-09-2019
7 | WB/RSHDP-II/EPC/02 | EOT NO-1 | 13-10-2018 | 05-02-2019 | 14-08-2019 | 02-02-2020
8 | WB/RSHDP-II/EPC/02 | EOT NO-2 | 13-10-2018 | 05-02-2019 | 14-12-2020 | 01-04-2021
9 | WB/RSHDP-II/EPC/02 | EOT NO-3 | 13-10-2018 | 05-02-2019 | 14-12-2020 | 04-04-2022
10 | WB/RSHDP-II/EPC/02 | ACHEIVED DATE | 01-01-2019 | 31-12-2019 | 14-12-2020 | 04-04-2022
11 | WB/RSHDP-II/EPC/03 | Contractual | 30-01-2019 | 30-05-2019 | 04-02-2020 | 02-08-2020
12 | WB/RSHDP-II/EPC/03 | EOT NO-1 | 30-01-2019 | 30-11-2020 | 31-10-2021 | 04-05-2022
13 | WB/RSHDP-II/EPC/03 | ACHEIVED DATE | 30-01-2019 | 30-11-2020 | 31-10-2021 | 04-05-2022
14 | WB/RSHDP-II/EPC/04 | Contractual | 00-00-2021 | 04-05-2022 | 16-09-2022 | 03-02-2023
15 | WB/RSHDP-II/EPC/04 | EOT NO-1 | 14-01-2022 | 04-05-2022 | 15-11-2022 | 27-11-2023
16 | WB/RSHDP-II/EPC/04 | EOT NO-2 | 14-01-2022 | 04-05-2022 | 15-11-2022 | 16-08-2024
17 | WB/RSHDP-II/EPC/04 | ACHEIVED DATE | 14-01-2022 | 04-05-2022 | 15-11-2022 | 16-08-2024
18 | WB/RSHDP-II/EPC/05 | Contractual | 16-07-2023 | 00-00-2023 | 16-04-2024 | 03-09-2024
19 | WB/RSHDP-II/EPC/05 | ACHEIVED DATE | 31-07-2023 | 20-10-2023 | 20-03-2024
20 | WB/RSHDP-II/EPC/06 | Contractual | 15-07-2023 | 07-11-2023 | 25-02-2024 | 19-06-2024
21 | WB/RSHDP-II/EPC/06 | ACHEIVED DATE | 04-08-2023 | 21-09-2023 | 20-12-2023 | 15-03-2024
22 | WB/ RSHDP II/ANNUITY 01 | Contractual | 27-01-2023 | 26-06-2023 | 29-09-2023 | 01-04-2024
23 | WB/ RSHDP II/ANNUITY 01 | ACHEIVED DATE | 27-01-2023 | 12-05-2023 | 13-12-2023 | 23-03-2024
24 | WB/ RSHDP II/ANNUITY 02 | Contractual | 02-06-2023 | 30-10-2023 | 02-02-2024 | 05-08-2024
25 | WB/ RSHDP II/ANNUITY 02 | EOT NO-1 | 30-09-2023 | 30-10-2023 | 02-02-2024 | 05-08-2024
26 | WB/ RSHDP II/ANNUITY 02 | ACHEIVED DATE | 30-09-2023 | 30-10-2023
27 | WB/ RSHDP II/ANNUITY 03 | Contractual | 27-01-2023 | 26-06-2023 | 29-09-2023 | 01-04-2024
28 | WB/ RSHDP II/ANNUITY 03 | EOT NO-1 | 27-01-2023 | 26-06-2023 | 29-09-2023 | 01-04-2024
29 | WB/ RSHDP II/ANNUITY 03 | ACHEIVED DATE | 27-02-2023 | 17-03-2023 | 07-11-2023
30 | WB/ RSHDP II/ANNUITY 04 | Contractual | 27-01-2023 | 26-06-2023 | 29-09-2023 | 01-04-2024
31 | WB/ RSHDP II/ANNUITY 04 | EOT NO-1 | 23-04-2023 | 24-07-2023 | 30-01-2024 | 02-08-2024
32 | WB/ RSHDP II/ANNUITY 04 | ACHEIVED DATE | 23-04-2023 | 24-07-2023
33 | RSHDP-II/WB-Tr-2/EPC-01 | Contractual | 26-08-2023 | 13-01-2024 | 27-05-2024 | 14-10-2024
34 | RSHDP-II/WB-Tr-2/EPC-02 | Contractual | 05-11-2023 | 28-02-2024 | 17-06-2024 | 10-10-2024
35 | RSHDP-II/WB-Tr-2/EPC-03 | Contractual | 26-08-2023 | 13-01-2024 | 27-05-2024 | 14-10-2024