## Table-1
Road Name: Khood DataramgarhRenwal (SH 8 A)
SN | Package No | Name of Highways | Contract Amount (INR Cr.) | Appointed date | Contract Amount after (COS) | Scheduled date of completion | Extended date of completion | EOT | Total awarded length (km) | Total length after COS (km) | Completed length (km) | Payment made excl. Price Adj. (Rs. Cr. | Physical progress in terms of Financial | Financial Progress based on actual expenditure | Date of completion (Date issue of provisional comp. certificate)
1 | WB/ RSHDP II/ANNUITY 04 | Ramseen Bhinmal Raniwara Road (SH 31) | 247.77 | 2022-09-29 | 247.77 | 2024-04-01 |  |  | 62.62 | 62.62 | 56.31 |  | 83.99 | 81.34
2 | WB/ RSHDP II/ANNUITY 03 | KishangarhArainMalpura (SH 07E & 101) | 130.66 | 2022-09-29 | 130.66 | 2023-12-27 |  |  | 66.95 | 66.95 | 65 |  | 73.82 | 99.95
3 | WB/ RSHDP II/ANNUITY 02 | Jhunjhunu Rajgarh (SH 41) | 140 | 2023-02-02 | 140 | 2024-08-05 |  |  | 62.73 | 62.73 | 58.33 |  | 75.36 | 145.99
4 | WB/ RSHDP II/ANNUITY 02 | NeemkathanaKhetriSinghana (SH 13) | 137 | 2023-02-02 | 137 | 2024-08-05 |  |  | 45.85 | 45.85 | 33.52 |  | 53.4 | 43.43
5 | WB/ RSHDP II/ANNUITY 01 | Sri Ganganagar Bikaner (Padampur Raisinghnagar & Sattasar Bikaner Section) (SH 03) | 195 | 2022-09-29 | 210.11 | 2024-04-01 |  |  | 93 | 93 | 81.47 |  | 87.23 | 100 | 2024-03-23
6 | WB/RSHDP-II/EPC/06 | Sayla Bagoda Guda Malani SH16B | 136 | 2023-03-22 | 136 | 2024-06-18 |  |  | 51 | 51 |  |  |  | 95.29 | 2024-03-15
7 | WB/RSHDP-II/EPC/05 | Bikaner Napasar Jasrasar SH20B | 157 | 2023-03-03 | 157 | 2024-09-03 | 03-09-2024 |  | 65.53 | 65.53 | 64.93 |  | 96.51 | 88.9
8 | WB/RSHDP-II/EPC/04 | Khood DataramgarhRenwal (SH 8 A) | 71 | 2021-08-02 | 71 | 2023-02-03 | 16-08-2024 |  | 51 | 51 | 4.93 | 35.34 | 15 | 49.77 | 2024-05-09
9 | WB/RSHDP-II/EPC/04 | ManglanaMakranaBorawad (SH 2B) including MakranaBidiyadParbatsar SH2D | 83 | 2021-08-02 | 83 | 2023-02-03 | 16-08-2024 |  | 38 | 38 | 21.564 |  | 2.13 | 82.7
10 | WB/RSHDP-II/EPC/04 | HurdaBanera (SH 39 A) | 87 | 2021-08-02 | 87 | 2023-02-03 | 16-08-2024 |  | 53 | 53 | 49.75 |  | 53.5 | 85.72
11 | WB/RSHDP-II/EPC/03 | Jodhpur Marwar Junction Jojawar (SH 61 & 61A) | 304.11 | 2018-08-03 | 304.11 | 2020-08-01 | 04-05-2022 |  | 119.1 | 119.1 | 116.9 |  | 93.44 | 97.56
12 | WB/RSHDP-II/EPC/02 | BhaviPiparKhimsar (SH 86 C) | 85 | 2018-06-20 | 101.74 | 2019-09-22 |  |  | 83.23 | 95 | 87.04 |  | 99.93 | 97.49
13 | WB/RSHDP-II/EPC/01 | Banar Bhopalgarh Kuchera (SH 63) | 207.11 | 2018-06-01 | 207.11 | 2019-09-03 |  |  | 126.5 | 126.5 | 126.14 |  | 93.65 | 96
14 | RSHDP-II/WB-Tr-2/EPC-01 | Mathania Tinwari Dechu (SH61B) &Jodhpur Tinwari (SH95) | 317.51 | 2023-04-13 | 317.51 | 2024-10-14 | 14-10-2024 |  | 108.4 | 108.4 | 101.556 |  | 86.56 | 0 | 0
15 | RSHDP-II/WB-Tr-2/EPC-02 | Rajgarh Bhadra (SH106) | 137.68 | 2023-07-13 | 137.68 | 2024-10-10 |  |  | 59.48 | 59.48 | 58.71 |  | 99.87 | 0
16 | RSHDP-II/WB-Tr-2/EPC-03 | Natni Ka Bara Malakhera Maujpur (SH44) | 105 | 2023-04-13 | 105 | 2024-10-14 |  |  | 25.7 | 25.7 | 23.74 |  | 67.99 | 0
17 | RHMP/WB/EPC-04 | Sathin Gotan | 81.04 |  | 81.04 |  |  |  | 30.4 | 30.4 |  |  | 0 | 0
18 | RHMP/HAM/01 | mal bamohari | 370 |  | 370 |  |  |  | 40.85 | 40.85 |  |  | 0 | 0

## Table-2
Road Name: Khood DataramgarhRenwal (SH 8 A)
SN | Item | Scope | Completed (Last month) | Inprogress (Last month) | Completed (This month) | Inprogress (This month) | Completed (Till Date) | Inprogress (Till Date) | Not Started (Till Date)
1 | Culvert | 14 | 9 |  |  |  | 9 | 0 | 5
2 | Major Junction | 5 | 1 |  |  |  | 1 | 0 | 4
3 | Minor Junction | 41 | 4 |  |  |  | 4 | 0 | 37
4 | Toll plaza | 1 | 1 |  |  |  | 1 | 0 | 0
5 | Bus shelter including Solar Light | 26 |  |  |  |  | 0 | 0 | 26
6 | Minor Bridge | 2 |  |  |  |  | 0 | 0 | 2

## Table-3
Road Name: Khood DataramgarhRenwal (SH 8 A)
SN | Item | Scope | Completed (Last month) | Completed (This month) | Completed (Till Date) | Balance
Reconstruction
1 | Sub grade | 6.2 | 0 |  | 0 | 6.2
2 | PQC | 6.2 | 2.5 |  | 2.5 | 3.7
3 | DLC | 6.2 | 0.01 |  | 0.01 | 6.19
Widening
1 | Sub grade | 20.33 | 4.7 |  | 4.7 | 15.63
2 | GSB | 20.33 | 4 | 1.2 | 5.2 | 15.13
3 | Base /WMM | 20.33 | 4 |  | 4 | 16.33
4 | DBM | 20.33 | 4 |  | 4 | 16.33
5 | BC | 20.33 | 2.43 |  | 2.43 | 17.9

## Table-4
Road Name: Khood DataramgarhRenwal (SH 8 A)
SN | Item | Scope | Completed (Last month) | Completed (This month) | Completed (Till Date) | Balance
1 | Sub grade | 40.7 | 4.7 |  | 4.7 | 36
2 | GSB | 50.74 | 4 | 1.2 | 5.2 | 45.54
3 | Base /WMM | 34.2 | 4 |  | 4 | 30.2
4 | DBM | 44.24 | 4 |  | 4 | 40.24
5 | BC | 44.24 | 2.43 |  | 2.43 | 41.81
6 | PQC | 6.5 | 2.5 |  | 2.5 | 4
7 | DLC | 6.5 | 0.01 |  | 0.01 | 6.49

## Table-5
Road Name: Khood DataramgarhRenwal (SH 8 A)
SN | Items | Cost as per schedule H (INR Cr.) | Executed till previous month (INR Cr.) | Progress During this month (INR Cr.) | Up to this month (INR Cr.) | Progress achieved (%)
1 | Road works, including culverts,widening and repair of culverts | 54.05 | 9.18 | 0.38 | 9.56 | 17.69
2 | Other Works | 16.95 | 1.09 |  | 1.09 | 6.44

## Table-6
Road Name: Khood DataramgarhRenwal (SH 8 A)
SN | Package | Awarded Amount | Payment (Last month) | Payment (This month) | Payment (Till Date) | Financial Progress (%)
1 | WB/RSHDP-II/EPC/04 | 241 |  | 35.34 | 35.34 | 14.66
2 | RHMP/HAM/01 | 370 |  |  | 0 | 0
3 | RHMP/WB/EPC-04 | 81.04 |  |  | 0 | 0
4 | RSHDP-II/WB-Tr-2/EPC-01 | 317.51 |  |  | 0 | 0
5 | RSHDP-II/WB-Tr-2/EPC-02 | 137.68 |  |  | 0 | 0
6 | RSHDP-II/WB-Tr-2/EPC-03 | 105 |  |  | 0 | 0
7 | WB/ RSHDP II/ANNUITY 01 | 210.11 |  |  | 0 | 0
8 | WB/ RSHDP II/ANNUITY 02 | 277 |  |  | 0 | 0
9 | WB/ RSHDP II/ANNUITY 03 | 130.66 |  |  | 0 | 0
10 | WB/ RSHDP II/ANNUITY 04 | 247.77 |  |  | 0 | 0
11 | WB/RSHDP-II/EPC/01 | 207.11 |  |  | 0 | 0
12 | WB/RSHDP-II/EPC/02 | 101.74 |  |  | 0 | 0
13 | WB/RSHDP-II/EPC/03 | 304.11 |  |  | 0 | 0
14 | WB/RSHDP-II/EPC/05 | 157 |  |  | 0 | 0
15 | WB/RSHDP-II/EPC/06 | 136 |  |  | 0 | 0

## Table-7
Road Name: Khood DataramgarhRenwal (SH 8 A)
SN | Road | Plantation | Survival
1 | Banar Bhopalgarh Kuchera (SH 63) | 1649 | 300
2 | Natni Ka Bara Malakhera Maujpur (SH44) | 1700 | 0

## Table-8
Road Name: Khood DataramgarhRenwal (SH 8 A)
SN | Package Name | Description | Milestone1 | Milestone2 | Milestone3 | Milestone4
1 | WB/RSHDP-II/EPC/01 | Contractual | 24-09-2018 | 17-01-2019 | 12-05-2019 | 04-09-2019
2 | WB/RSHDP-II/EPC/01 | EOT NO-1 | 24-09-2018 | 17-01-2019 | 12-05-2019 | 05-11-2019
3 | WB/RSHDP-II/EPC/01 | EOT NO-2 | 01-05-2019 | 01-11-2019 | 02-09-2020 | 13-06-2020
4 | WB/RSHDP-II/EPC/01 | EOT NO-3 | 01-05-2019 | 01-11-2019 | 18-11-2020 | 19-10-2020
5 | WB/RSHDP-II/EPC/01 | ACHEIVED DATE | 01-05-2019 | 01-11-2019 | 18-11-2020 | 19-10-2020
6 | WB/RSHDP-II/EPC/02 | Contractual | 13-10-2018 | 05-02-2019 | 14-08-2019 | 23-09-2019
7 | WB/RSHDP-II/EPC/02 | EOT NO-1 | 13-10-2018 | 05-02-2019 | 14-08-2019 | 02-02-2020
8 | WB/RSHDP-II/EPC/02 | EOT NO-2 | 13-10-2018 | 05-02-2019 | 14-12-2020 | 01-04-2021
9 | WB/RSHDP-II/EPC/02 | EOT NO-3 | 13-10-2018 | 05-02-2019 | 14-12-2020 | 04-04-2022
10 | WB/RSHDP-II/EPC/02 | ACHEIVED DATE | 01-01-2019 | 31-12-2019 | 14-12-2020 | 04-04-2022
11 | WB/RSHDP-II/EPC/03 | Contractual | 30-01-2019 | 30-05-2019 | 04-02-2020 | 02-08-2020
12 | WB/RSHDP-II/EPC/03 | EOT NO-1 | 30-01-2019 | 30-11-2020 | 31-10-2021 | 04-05-2022
13 | WB/RSHDP-II/EPC/03 | EOT NO-2 | 30-01-2019 | 30-11-2020 | 31-10-2021 | 04-05-2022
14 | WB/RSHDP-II/EPC/03 | ACHEIVED DATE | 30-01-2019 | 30-11-2020 | 31-10-2021 | 04-05-2022
15 | WB/RSHDP-II/EPC/04 | Contractual | 00-00-2021 | 04-05-2022 | 16-09-2022 | 03-02-2023
16 | WB/RSHDP-II/EPC/04 | EOT NO-1 | 14-01-2022 | 04-05-2022 | 15-11-2022 | 27-11-2023
17 | WB/RSHDP-II/EPC/04 | EOT NO-2 | 14-01-2022 | 04-05-2022 | 15-11-2022 | 16-08-2024
18 | WB/RSHDP-II/EPC/04 | ACHEIVED DATE | 14-01-2022 | 04-05-2022 | 15-11-2022 | 16-08-2024
19 | WB/RSHDP-II/EPC/05 | Contractual | 16-07-2023 | 03-12-2023 | 16-04-2024 | 03-09-2024
20 | WB/RSHDP-II/EPC/05 | EOT NO-1 | 16-07-2023 | 03-12-2023 | 16-04-2024 | 03-09-2024
21 | WB/RSHDP-II/EPC/05 | ACHEIVED DATE | 31-07-2023 | 20-10-2023 | 20-03-2024 | 02-08-2024
22 | WB/RSHDP-II/EPC/06 | Contractual | 15-07-2023 | 07-11-2023 | 25-02-2024 | 19-06-2024
23 | WB/RSHDP-II/EPC/06 | ACHEIVED DATE | 04-08-2023 | 21-09-2023 | 20-12-2023 | 15-03-2024
24 | WB/ RSHDP II/ANNUITY 01 | Contractual | 27-01-2023 | 26-06-2023 | 29-09-2023 | 01-04-2024
25 | WB/ RSHDP II/ANNUITY 01 | ACHEIVED DATE | 27-01-2023 | 12-05-2023 | 13-12-2023 | 23-03-2024
26 | WB/ RSHDP II/ANNUITY 02 | Contractual | 02-06-2023 | 30-10-2023 | 02-02-2024 | 05-08-2024
27 | WB/ RSHDP II/ANNUITY 02 | EOT NO-1 | 30-09-2023 | 30-10-2023 | 02-02-2024 | 05-08-2024
28 | WB/ RSHDP II/ANNUITY 02 | ACHEIVED DATE | 30-09-2023 | 30-10-2023
29 | WB/ RSHDP II/ANNUITY 03 | Contractual | 27-01-2023 | 26-06-2023 | 29-09-2023 | 01-04-2024
30 | WB/ RSHDP II/ANNUITY 03 | EOT NO-1 | 27-01-2023 | 26-06-2023 | 29-09-2023 | 01-04-2024
31 | WB/ RSHDP II/ANNUITY 03 | ACHEIVED DATE | 27-02-2023 | 17-03-2023 | 07-11-2023
32 | WB/ RSHDP II/ANNUITY 04 | Contractual | 27-01-2023 | 26-06-2023 | 29-09-2023 | 01-04-2024
33 | WB/ RSHDP II/ANNUITY 04 | EOT NO-1 | 23-04-2023 | 24-07-2023 | 30-01-2024 | 02-08-2024
34 | WB/ RSHDP II/ANNUITY 04 | ACHEIVED DATE | 23-04-2023 | 24-07-2023
35 | RSHDP-II/WB-Tr-2/EPC-01 | Contractual | 26-08-2023 | 13-01-2024 | 27-05-2024 | 14-10-2024
36 | RSHDP-II/WB-Tr-2/EPC-01 | EOT NO-1 | 26-08-2023 | 13-01-2024 | 27-05-2024 | 14-10-2024
37 | RSHDP-II/WB-Tr-2/EPC-02 | Contractual | 05-11-2023 | 28-02-2024 | 17-06-2024 | 10-10-2024
38 | RSHDP-II/WB-Tr-2/EPC-03 | Contractual | 26-08-2023 | 13-01-2024 | 27-05-2024 | 14-10-2024
39 | WB/Road One | Contractual | NaN-00-,Na | -00-,NaN-0 | -,NaN-00-
40 | WB/Road One | ACHEIVED DATE | 16-07-2025 | 17-07-2025 | 16-07-2025 | 15-07-2025